{"text_format":"3","workbook":"xls","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"images":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":205,"n_cols":8,"rows_kept":205,"merged":[[0,0,14,7],[15,0,15,1],[15,2,15,7],[16,0,16,1],[16,2,16,7],[17,0,17,1],[17,2,17,7],[18,0,18,1],[18,2,18,7],[21,1,21,6],[22,0,22,7],[24,1,24,6],[25,0,62,7],[63,1,63,6],[64,1,64,6],[65,2,65,3],[66,2,66,3],[67,0,76,0],[67,2,67,3],[68,2,68,3],[69,2,69,3],[70,2,70,3],[71,2,71,3],[72,2,72,3],[73,2,73,3],[74,2,74,3],[75,2,75,3],[76,2,76,3],[77,0,81,0],[77,2,77,3],[78,2,78,3],[79,2,79,3],[80,2,80,3],[81,2,81,3],[82,0,85,0],[82,2,82,3],[83,2,83,3],[84,2,84,3],[85,2,85,3],[86,2,86,3],[87,0,101,0],[87,2,87,3],[88,2,88,3],[89,2,89,3],[90,2,90,3],[91,2,91,3],[92,2,92,3],[93,2,93,3],[94,2,94,3],[95,2,95,3],[96,2,96,3],[97,2,97,3],[98,2,98,3],[99,2,99,3],[100,2,100,3],[101,2,101,3],[102,2,102,3],[103,0,104,0],[103,2,103,3],[104,2,104,3],[105,0,111,0],[105,2,105,3],[106,2,106,3],[107,2,107,3],[108,2,108,3],[109,2,109,3],[110,2,110,3],[111,2,111,3],[112,2,112,3],[113,2,113,3],[113,11,113,12],[114,0,116,0],[114,2,114,3],[115,2,115,3],[116,2,116,3],[117,0,119,0],[117,2,117,3],[118,2,118,3],[119,2,119,3],[120,0,124,0],[120,2,120,3],[121,2,121,3],[122,2,122,3],[123,2,123,3],[124,2,124,3],[125,2,125,3],[126,0,132,0],[126,2,126,3],[127,2,127,3],[128,2,128,3],[129,2,129,3],[130,2,130,3],[131,2,131,3],[132,2,132,3],[133,2,133,3],[134,2,134,3],[135,2,135,3],[136,2,136,3],[137,0,139,0],[137,2,137,3],[138,2,138,3],[139,2,139,3],[140,0,141,0],[140,2,140,3],[141,2,141,3],[142,0,158,0],[142,2,142,3],[143,2,143,3],[144,2,144,3],[145,2,145,3],[146,2,146,3],[147,2,147,3],[148,2,148,3],[149,2,149,3],[150,2,150,3],[151,2,151,3],[152,2,152,3],[153,2,153,3],[154,2,154,3],[155,2,155,3],[156,2,156,3],[157,2,157,3],[158,2,158,3],[159,2,159,3],[160,2,160,3],[161,0,168,0],[161,2,161,3],[162,2,162,3],[163,2,163,3],[164,2,164,3],[165,2,165,3],[166,2,166,3],[167,2,167,3],[168,2,168,3],[169,2,169,3],[170,2,170,3],[171,2,171,3],[172,2,172,3],[174,1,174,6],[176,1,176,6],[177,2,177,3],[178,2,178,3],[180,1,180,6],[181,2,181,3],[182,2,182,3],[183,0,184,0],[183,2,183,3],[184,2,184,3],[185,0,188,0],[185,2,185,3],[186,2,186,3],[187,2,187,3],[188,2,188,3],[189,2,189,3],[198,1,198,6],[200,0,200,1],[200,2,200,3],[200,5,200,7],[201,0,201,1],[201,2,201,7],[202,0,202,1],[202,2,202,7],[203,0,203,1],[203,2,203,7],[204,0,204,1],[204,2,204,7]],"flags":["formulas_cached_only"]}
["建 设 工 程 材 料\n\n 送 检 计 划 书"]
{"$rows_empty":14}
["工程名称：",null,"三峡柑橘忠县鲜果集散处理基地项目（渝东北农副产品及进出口肉类冷链加工集配中心一期）"]
["建设单位：",null,"重庆三峡柑橘集团忠县果业有限公司"]
["监理单位：",null,"重庆市五环工程建设管理有限公司"]
["施工单位：",null,"重庆宏耀建设（集团）有限公司"]
[]
[]
[null,"忠县建设工程质量检测站制"]
["    说明：送检计划书（另附单位工程用量清单）在建设单位办理委托检测合同时，由建设单位或施工单位负责填写；建设、监理单位签署意见报送监督机构审查。计划书一式五份，建设、监理、施工、监督单位、检测单位各一份。"]
[]
[null,"工程概况"]
["1、工程综合说明\n    工程名称：三峡柑橘忠县鲜果集散处理基地项目（渝东北农副产品及进出口肉类冷链加工集配中心一期）\n    建设单位：重庆三峡柑橘集团忠县果业有限公司\n    设计单位：中机中联工程有限公司\n    地勘单位：四川名阳岩土工程有限公司\n    监理单位：重庆市五环工程建设管理有限公司\n    施工单位：重庆宏耀建设（集团）有限公司\n    质量监督单位：忠县建设工程质量中心\n    安全监督单位：忠县建设工程施工安全管理站\n    工程地址：忠县新生港\n\n2、工程项目组成\n    重庆宏耀建设（集团）有限公司生产三峡柑橘忠县鲜果集散处理基地项目（渝东北农副产品及进出口肉类冷链加工集配中心一期）项目\n\n3、建筑工程概况\n    本项目厂房建筑面积约 9100平方米，主要跨度约 32.1米，设备机房建筑面积约 900平方米。给排水、电气、暖通、消防等。工程造价：1999.948366万元。"]
{"$rows_empty":37}
[null,"建设工程材料送检计划明细表"]
[null,"基础、主体分部工程"]
["检测\n项目","型号\n规格","使用\n部位\n",null,"工程\n总用量","送检\n批量","单价（元）","总价（元）"]
["基岩","50*100mm","1号车间设、备机房",null,"/","/","/","/"]
["钢筋","HRB400E（25mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E（22mm)","设备机房",null,"/","/","/","/"]
[null,"HRB400E（20mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E（18mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E（16mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E（14mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E（12mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HPB300（10mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HPB300（8mm)","1号车间、设备机房",null,"/","/","/","/"]
[null,"HPB300（6mm)","1号车间、设备机房",null,"/","/","/","/"]
["钢筋连接工艺检测","HRB400E(25mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(18mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(16mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(14mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(12mm）","1号车间、设备机房",null,"/","/","/","/"]
["钢筋连接检测","HRB400E(12mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(14mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(16mm）","1号车间、设备机房",null,"/","/","/","/"]
[null,"HRB400E(18mm）","1号车间、设备机房",null,"/","/","/","/"]
["声测管",null,"1号车间",null,null,1]
["管材","聚乙烯塑料复合管DN100","1号车间、设备机房",null,null,1]
[null,"聚乙\n烯塑料复合管\nDN150","1号车间、设备机房",null,null,1]
[null,"聚乙烯塑料复合管DN200","1号车间、设备机房",null,null,1]
[null,"PVC双壁波纹管D110","2号车间、设备机房",null,null,1]
[null,"HDPE双壁波纹管D200","1号车间、设备机房",null,null,1]
[null,"HDPE双壁波纹管D300","1号车间、设备机房",null,null,1]
[null,"HDPE双壁波纹管D400","1号车间、设备机房",null,null,1]
[null,"HDPE双壁波纹管D500","1号车间、设备机房",null,null,1]
[null,"镀锌钢管SC100","1号车间、设备机房",null,null,1]
[null,"镀锌钢管SC150","1号车间、设备机房",null,null,1]
[null,"PPR（S5系列）DN15","1号车间、设备机房",null,null,1]
[null,"PPR（S5系列）DN20","1号车间、设备机房",null,null,1]
[null,"PPR（S5系列）DN25","1号车间、设备机房",null,null,1]
[null,"PPR（S5系列）DN32","1号车间、设备机房",null,null,1]
[null,"钢塑复合管DN50","1号车间、设备机房",null,null,1]
["钢筋焊接网",null,"1号车间、设备机房",null,null,1]
["砌块","蒸压加气混凝土砌块","1号车间、设备机房",null,"/","/","/","/"]
[null,"MU15混凝土砌块","1号车间、设备机房",null,"/","/","/","/"]
["混凝土试件","C10","井",null,"/","/","/","/"]
[null,"C15","围墙垫层",null,"/","/","/","/"]
[null,"C20","1号车间、设备机房、围墙",null,"/","/","/","/"]
[null,"C25","设备机房、井、围墙",null,"/","/","/","/"]
[null,"C30","1号车间",null,"/","/","/","/"]
[null,"C30P6","1号车间、设备机房",null,"/","/","/","/"]
[null,"C40微膨胀","1号车间",null,"/","/","/","/"]
["砂","特细砂","1号车间、设备机房",null,"/","/","/","/"]
["水泥","普通硅酸盐水泥42.5","1号车间、设备机房",null,"/","/","/","/"]
["砂浆配合比","M7.5","1号车间、设备机房",null,"/","/","/","/"]
[null,"M10","井",null,"/","/","/","/"]
[null,"M5","1号车间、设备机房",null,"/","/","/","/"]
["砂浆试件","M7.5水泥砂浆","1号车间、设备机房",null,"/","/","/","/"]
[null,"M5水泥砂浆","1号车间、设备机房",null,"/","/","/","/"]
[null,"M10水泥砂浆","井",null,"/","/","/","/"]
["钢板",6.7,"1号车间",null,null,1]
[null,8.9,"1号车间",null,null,1]
[null,10.11,"1号车间",null,null,1]
[null,12,"1号车间",null,null,1]
[null,"工字钢","1号车间",null,null,4]
["圆钢","∅22","1号车间",null,null,1]
["锚栓","M24（扭矩系数）","1号车间",null,null,1]
[null,"M30","1号车间",null,null,1]
[null,"M27","1号车间",null,null,1]
[null,"M22","1号车间",null,null,1]
[null,"M20","1号车间",null,null,1]
[null,"M16","1号车间",null,null,1]
[null,"M12","1号车间",null,null,1]
["焊缝探伤","现场检测","1号车间、设备机房",null,null,"检测总焊缝数的20%"]
["防火涂料","防火涂料","1号车间、设备机房",null,null,3]
["涂层厚度","现场检测","1号车间、设备机房",null,null,{"v":0.1,"d":"10%"}]
["栏杆水平推力","现场检测","1号车间、设备机房",null,null,"1组"]
["基础检测","超声波检测桩体完整性类别","1号车间、设备机房",null,null,"15~20%"]
[null,"超声波检测桩体完整性类别","1号车间、设备机房",null,null,92]
[null,"压实度检测现场检测","1号车间、设备机房、道路",null,"/","/","/","/"]
["主体结构实体检测","现场检测（强度、保护层厚度）","1号车间、设备机房、道路",null,"/","/","/","/"]
[null,"设计要求提供沉降观测记录","1号车间、设备机房、道路",null,null,1]
["电气工程","电力电缆ZC-YJV-4x185","1号车间、设备机房",null,null,1]
[null,"电气配线BVV-2.5","1号车间、设备机房",null,null,1]
[null,"电气配线ZB-BV-2.5","1号车间、设备机房",null,null,1]
[null,"电气配线ZB-BV-4","1号车间、设备机房",null,null,1]
[null,"电气配线BVV-4","1号车间、设备机房",null,null,1]
[null,"ZN-RVS-2*1.5","1号车间（消防）",null,null,1]
[null,"ZN-RVS-2*2.5","1号车间（消防）",null,null,"1组"]
[null,"ZN-RVVP-2*1.5","1号车间（消防）",null,null,1]
[null,"ZN-RVVSP-2*1.0","1号车间（消防）",null,null,1]
[null,"ZN-RYJ-2*1.5","1号车间（消防）",null,null,1]
[null,"ZN-BV-2.5mm2","1号车间（消防）",null,null,1]
[null,"NH-BV-6mm2","1号车间（消防）",null,null,1]
[null,"电气配管JDG管-\n20","1号车间、设备机房",null,null,1]
[null,"电气配管-SC25","1号车间、设备机房",null,null,1]
[null,"电气配管-SC100","1号车间、设备机房",null,null,1]
[null,"角钢","1号车间、设备机房",null,null,1]
[null,"扁钢","1号车间、设备机房",null,null,1]
["建筑物防雷接地性能检测","现场检测--接地电阻","1号车间、设备机房",null,null,1]
["消防检测","现场检测","1号车间、设备机房",null,null,1]
["保温系统","保温板（地面、屋面、外墙）","设备机房",null,null,3]
[null,"耐碱网布","设备机房",null,null,2]
[null,"胶粘剂","设备机房",null,null,1]
[null,"保温砂浆","设备机房",null,null,4]
[null,"锚栓（原材、抗拔）","设备机房",null,null,2]
[null,"实体检测","设备机房",null,null,1]
[null,"照明功率密度（现场实体检测）","1号车间、设备机房",null,null,1]
[null,"平均照度（现场实体检测）","1号车间、设备机房",null,null,1]
["井盖",null,"室外",null,null,1]
["透水砖",null,"室外",null,null,1]
["路缘石",null,"室外",null,null,1]
["水质检测",{"$nulls":4},1]
[]
["合计"]
[]
[null,"屋面分部工程"]
["检测\n项目","型号\n规格","使用\n部位\n",null,"工程\n总用量","送检\n批量","单价（元）","总价（元）"]
["防水材料","4mm聚脂胎SBS改性沥青卷材","设备机房",null,"/","/","/","/"]
["屋面小计"]
[null,"装饰装修分部工程"]
["检测\n项目","型号\n规格","使用\n部位\n",null,"工程\n总用量","送检\n批量","单价（元）","总价（元）"]
["防水涂料",null,"设备机房",null,null,2]
["门窗","四性检测",{"$nulls":3},1]
[null,"型材检测",{"$nulls":3},1]
["玻璃","传热系数、",{"$nulls":3},1]
[null,"可见光透射比、",{"$nulls":3},1]
[null,"遮阳系数",{"$nulls":3},1]
[null,"露点检测",{"$nulls":3},1]
[]
["装饰修小计"]
{"$rows_empty":7}
[null,"建设工程材料送检审核表"]
[]
["编制人员",null,"（施工单位编制）",null,"联系电话"]
["审核人员",null,"（监理单位和建设单位审核）"]
["施工单位",null,"\n\n技术负责人：（签字）\n\n\n\n联系电话：\n\n\n                                             （公章）\n\n                                        年      月      日"]
["监理单位",null,"\n\n项目总监理工程师：（签字）\n\n\n\n联系电话：\n\n\n                                              （公章）\n\n                                       年      月      日"]
["建设单位",null,"\n\n项目负责人：（签字）\n\n\n\n联系电话：\n\n\n                                              （公章）\n\n                                        年      月      日"]